|  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| # | Task | Sprint | Responsible | Start | End | Days | hours | Status |
| 1 | Planning home page | One | Saga Mohamed / Alaa Eid | 28/2 | 3/3 | 4 | 20 | Delayed |
| 2 | Documentation template for the website | One | Kholoud Singab / Esraa Eid | 4/3 | 10/3 | 10 | 30 | Delayed |
| 3 | Design logo of the website | One | Esraa Shata /Sarah Tarek | 11/3 | 14/3 | 4 | 18 | Delayed |
| 4 | Analysis home page | Two | Esraa Shata /Sarah Tarek | 18/3 | 23/3 | 6 | 15 | Complete |
| 5 | Analysis properties page | Two | Saga Mohamed / Alaa Eid | 18/3 | 23/3 | 6 | 15 | On track |
| 6 | Design search bar | Two | Sarah Tarek | 24/3 | 25/3 | 1 | 3 | On track |
| 7 | Design follow us | Two | Esraa shata | 24/3 | 25/3 | 1 | 3 | On track |
| 8 | Design navigation bar | Two | Esaraa shata | 25/3 | 26/3 | 1 | 3 | On track |
| 9 | Design slider | Two | Sarah tarek | 25/3 | 26/3 | 1 | 3 | On track |
| 10 | Design multiple choices properties | Two | Saga Mohame / Alaa Eid |  |  |  |  | On track |
| 11 | Code home page | Two | Esraa Shata /Sarah Tarek | 27/3 | 30/3 | 4 | 21 | On track |
| 12 | Code properties page | Two | Saga Mohamed / Alaa Eid | 27/3 | 30/3 | 4 | 21 | On track |
| 13 | Test properties page | Two | Saga Mohamed / Alaa Eid | 31/3 | 1/4 | 2 | 16 | On track |
| 14 | Test home page | Two | Esraa Shata /Sarah Tarek | 31/3 | 1/4 | 2 | 16 | On track |
| 15 | Search bar option | Two | Kholoud Singab / Esraa Eid | 18/3 | 31/3 | 7 | 17 | On track |
| 16 | Analysis buying page | Three | Esraa Shata /Sarah Tarek | 2/4 | 7/4 | 6 | 23 | Behind |
| 17 | Analysis rent page | Three | Saga Mohamed / Alaa Eid | 2/4 | 7/4 | 6 | 23 | Behind |
| 18 | Design multiple choices properties | Three | Esraa Shata /Sarah Tarek | 8/4 | 10/4 | 3 | 30 | Behind |
| 19 | Design multiple choices properties | Three | Saga Mohamed / Alaa Eid | 8/4 | 10/4 | 3 | 30 | Behind |
| 20 | Code buying page | Three | Esraa Shata /Sarah Tarek | 11/4 | 14/4 | 4 | 15 | Behind |
| 21 | Code rent page | Three | Saga Mohamed / Alaa Eid | 11/4 | 14/4 | 4 | 15 | Behind |
| 22 | Test buying page | Three | Esraa Shata /Sarah Tarek | 15/4 | 16/4 | 2 | 22 | Behind |
| 23 | Test rent page | Three | Saga Mohamed / Alaa Eid | 15/4 | 16/4 | 2 | 22 | Behind |
| 24 | search classifying | Four | Kholoud Singab / Esraa Eid | 17/4 | 19/4 | 3 | 24 | Behind |
| 25 | Footer design | Four | Esraa Shata /Sarah Tarek | 24/4 | 27/4 | 4 | 33 | Behind |
| 26 | Footer coding | Four | Esraa Shata /Sarah Tarek | 24/4 | 27/4 | 4 | 33 |  |
| 27 | Navigation bar design | Four | Saga Mohamed / Alaa Eid | 28/4 | 30/4 | 3 | 15 | Behind |
| 28 | Navigation bar coding | Four | Saga Mohamed / Alaa Eid | 28/4 | 30/4 | 3 | 15 | Behind |
| 29 | Data base building | Four | Kholoud Singab / Esraa Eid | 20/4 | 21/4 | 1 | 11 | Behind |
| 30 | Search request design and coding | Four | Kholoud Singab / Esraa Eid | 22/4 | 23/4 | 1 | 9 | Behind |

|  |  |  |  |
| --- | --- | --- | --- |
| Sprint 1 | | | |
| Date : From 28/2/2018 To 14/3/2018 | | | |
| # | **Task** | **Responsible** | **State** |
| 1 | Planning home page | Saga Mohamed / Alaa Eid | Delayed |
| 2 | Documentation template for the website | Kholoud Singab / Esraa Eid | Delayed |
| 3 | Design logo of the website | Esraa Shata /Sarah Tarek | Delayed |

|  |  |  |  |
| --- | --- | --- | --- |
| Sprint 2 | | | |
| Date : From 18/3/2018 To 1/4/2018 | | | |
| # | Task | Responsible | State |
| 1 | Home page analysis | Esraa Shata /sarah tarek | Complete |
| 2 | Search bar design | Sarah Tarek | On track |
| 3 | Follow us design | Esraa shata | On track |
| 4 | Navigation bar design | Esraa shata | On track |
| 5 | Slider design | Sarah tarek | On track |
| 6 | Home page coding | Esraa Shata /Sarah Tarek | On track |
| 7 | test | Esraa Shata /Sarah Tarek | On track |
| 8 | Properties page analysis | Saga Mohamed / Alaa Eid | Complete |
| 9 | Multiple choices properties design | Saga Mohamed / Alaa Eid | On track |
| 10 | Properties page coding | Saga Mohamed / Alaa Eid | On track |
| 11 | test | Saga Mohamed / Alaa Eid | On track |
| 12 | Search bar analysis | Kholoud Singab / Esraa Eid | Complete |
| 13 | Search bar design | Kholoud Singab / Esraa Eid | On track |
| 14 | Search bar coding | Kholoud Singab / Esraa Eid | On track |
| 15 | test | Kholoud Singab / Esraa Eid | On track |

|  |  |  |  |
| --- | --- | --- | --- |
| Sprint 3 | | | |
| Date : From 2/4/2018 To 16/4/2018 | | | |
| # | **Task** | **Responsible** | **State** |
| 1 | Analysis buying page | Esraa Shata /Sarah Tarek | Behind |
| 2 | Design Multiple choices properties | Esraa Shata /Sarah Tarek | Behind |
| 3 | Coding buying page | Esraa Shata /Sarah Tarek | Behind |
| 4 | Testing | Esraa Shata /Sarah Tarek | Behind |
| 5 | Analysis rent page | Saga Mohamed / Alaa Eid | Behind |
| 6 | Design Multiple choices properties | Saga Mohamed / Alaa Eid | Behind |
| 7 | Coding rent page | Saga Mohamed / Alaa Eid | Behind |
| 8 | Testing | Saga Mohamed / Alaa Eid | Behind |

|  |  |  |  |
| --- | --- | --- | --- |
| Sprint 4 | | | |
| Date : From 17/4/2018 To 1/5/2018 | | | |
| # | **Task** | **Responsible** | **State** |
| 1 | Search classifying | Kholoud Singab / Esraa Eid | Behind |
| 2 | Footer design | Esraa Shata /Sarah Tarek | Behind |
| 3 | Footer coding | Esraa Shata /Sarah Tarek | Behind |
| 4 | Navigation bar design | Saga Mohamed / Alaa Eid | Behind |
| 5 | Navigation bar coding | Saga Mohamed / Alaa Eid | Behind |
| 6 | Data base building | Kholoud Singab / Esraa Eid | Behind |
| 7 | Search request | Kholoud Singab / Esraa Eid | Behind |